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Night-time activities and start of work on in the ground shaped walls (CSM - Cutter Soil Mix walls) and piled foundations.
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2 januari 2017
Referentie
1701-0208
Project
15055 Ondergrondse fietsenstalling kon. Julianaplein, Den Haag, DEN HAAG
Behandeld door
Karina Wilting
E-mail
k.wilting@ mobilis.nl
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[bookmark: bmBegin][bookmark: _GoBack]The construction site on the Koningin Julianaplein is almost ready for the start of construction work on the underground cycle store. During the night-time hours between the 9th and 10th of January, Mobilis will adapt the entry of our construction site to make it suitable for the construction traffic.
Work on the construction of the underground CSM walls will start on January 16th followed by the installation of the piled foundations on January 30th . 

Schedule 
The CSM walls will run around the periphery of the site and will form the construction pit. This pit will ensure that the ground can safely be excavated later in the process.  The construction of Cutter Soil Mix walls is a low-noise, vibration-free process. A machine excavates and turns over the soil, simultaneously adding a binding agent (cement) and water. The mixture sets to form a robust wall. The CSM wall on the Stichthage side will also form part of the structure of the cycle store. Work on the CSM walls will continue for eight weeks. Mobilis will be working on the CSM walls only on weekdays, not at weekends.

Mobilis will make a start on the piling work 2 weeks after work starts on the CSM  walls, in week 5. The foundation piles will be screwed into the ground rather than being driven. Several machines will be employed simultaneously on the construction of the pilings. This too is a low-noise, vibration-free construction method. The work is expected to continue from January 30th  to the end of April. 

In summary:
Night-time activities: January 9th 22.00h until January 10th 05.00h
Construction of CSM walls: 16 January 2017 - end of March 2017
Construction of foundation piles: 30th  January 2017 – end of April 2017

Surrounding area
For a brief period during the construction of the CSM walls and part of the piling work pedestrians and cyclists coming from the Bezuidenhoutseweg will be diverted through a tunnel. The pedestrian route on the Stichthage side will not be open on every moment during the construction of the CSM wall.

Contact details
Please feel free to contact us with any questions about this letter. You can use the contact form on our website www.kj-plein.nl, or by email at info@kj-plein.nl. If you see anything unexpected or if you wish to report an incident/emergency you can contact us 24/7 on our emergency number: 06-21504617. 

With kind regards,
[image: ]

Mrs Ir. C. T. Davidse
Environmental Manager, Mobilis
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